## ControlPoints
Index | SubjectMatterId | ControlId | Type | Activity | Acceptance Criteria | Time | Method | Documentation Requirements | Scope | Note | Language
KP00_1_ProcessEN | KP00 | 1 | Process | Access and Transport Routes | Free of Materials, Waste, and Machines, etc. | Weekly Inspection | Visual | Photo | 20 % |  | EN
KP00_2_ProcessEN | KP00 | 2 | Process | Barriers | Intact barriers | Weekly Inspection | Visual | Photo |  |  | EN
KP00_3_ProcessEN | KP00 | 3 | Process | Lighting - orientation lights, work lights | Functional, Lux requirements met | Weekly Inspection | Visual | Photo |  |  | EN
KP00_4_ProcessEN | KP00 | 4 | Process | Construction site layout | Appropriate site facilities | Weekly Inspection | Visual | Photo |  |  | EN
KP00_5_ProcessEN | KP00 | 5 | Process | Construction power, -panels, cables etc. | Undamaged, suspended, approved. | Weekly Inspection | Visual | Photo |  |  | EN
KP00_6_ProcessEN | KP00 | 6 | Process | Ergonomics and behavior | Suitable technical aids used | Weekly Inspection | Visual | Photo |  |  | EN
KP00_7_ProcessEN | KP00 | 7 | Process | Vehicles | Tidy, materials are protected against weather impact | Weekly Inspection | Visual | Photo |  |  | EN
KP00_8_ProcessEN | KP00 | 8 | Process | Material storage and handling | Tidy, materials are protected against weather impact | Weekly Inspection | Visual | Photo |  |  | EN
KP00_9_ProcessEN | KP00 | 9 | Process | Machinery | Approved, and correct safety measures | Weekly Inspection |  |  |  |  | EN
KP00_10_ProcessEN | KP00 | 10 | Process | Order and tidiness | Adequately cleaned up | Weekly Inspection |  |  |  |  | EN
KP00_11_ProcessEN | KP00 | 11 | Process | Railings and barriers | Complete, railings where required. | Weekly Inspection |  |  |  |  | EN
KP00_12_ProcessEN | KP00 | 12 | Process | Signage | Appropriate signage, with mandatory notices etc. | Weekly Inspection |  |  |  |  | EN
KP00_13_ProcessEN | KP00 | 13 | Process | Scaffolding, lifts, ladders | Approved, and signage | Weekly Inspection |  |  |  |  | EN
KP00_14_ProcessEN | KP00 | 14 | Process | Excavations | Shielding | Weekly Inspection |  |  |  |  | EN
KP00_15_ProcessEN | KP00 | 15 | Process | Welfare measures | Appropriate for the number of personnel on site, first aid equipment fulfilled | Weekly Inspection |  |  |  |  | EN
KP00_16_ProcessEN | KP00 | 16 | Process | Construction site fence | Complete fence, damaged Sections replaced as necessary | Weekly Inspection |  |  |  |  | EN
KP00_17_ProcessEN | KP00 | 17 | Process | Common area + Common access routes | Separation of pedestrians/vehicles Traffic. | Weekly Inspection |  |  |  |  | EN
KP01_1_ReceiveEN | KP01 | 1 | Receive | Materials, deliveries, dimensions, delivery notes | Control of deliveries matches the project material | Upon delivery | Visual, measurement | Photo | 100 % |  | EN
KP01_2_ReceiveEN | KP01 | 2 | Receive | Takeovers after another contractor | Control of surfaces, boundaries, sections, or rooms | Upon takeover of boundary surfaces | Visual, measurement | Photo | 100 % |  | EN
KP01_3_ReceiveEN | KP01 | 3 | Receive | Damages | Inspections are carried out on deliveries for damages | Upon receipt | Visual | Photo | 100 % |  | EN
KP01_4_ProcessEN | KP01 | 4 | Process | Manholes, pump manholes, grease separators, others | Levels, height indications, placement, covers, connections. | Under construction | Visual | Photo, measurement, placement | 20 % |  | EN
KP01_5_ProcessEN | KP01 | 5 | Process | Fill around manholes | It must be ensured that the fill around the area is documented and compacted. | Under construction | Visual | Photo, measurement, placement | 25 % |  | EN
KP01_6_ProcessEN | KP01 | 6 | Process | Wires/drains executed in the ground sewer | Indication of slope, executed joints, connections. | Under construction | Visual | Photo, measurement, placement | 75 % |  | EN
KP01_7_ProcessEN | KP01 | 7 | Process | For filling around wires with suitable and draining material. Drainage/stormwater pipe | It must be ensured that suitable fill is documented and compacted. | Under construction | Visual | Photo, measurement, placement | 75 % |  | EN
KP01_8_ProcessEN | KP01 | 8 | Process | Excavations | Control of depth and width, levels | Under construction | Visual | Photo, measurement, placement | 75 % |  | EN
KP01_9_ProcessEN | KP01 | 9 | Process | Proctor tests, compaction control | All places where predetermined coverings/asphalt etc. | Under construction | Visual | Photo, measurement, placement | 100% |  | EN
KP01_10_ProcessEN | KP01 | 10 | Process | Surface water/drainage executed on the ground | Levels, height indications, placement, connections, fall from buildings, fall etc. | Under construction | Visual | Photo, measurement, placement | 75 % |  | EN
KP01_11_ProcessEN | KP01 | 11 | Process | Socket drains, battery edges | Edge casting, connections, setting layer, pre-casting | Under construction | Visual | Photo, measurement, placement | 75 % |  | EN
KP01_12_ProcessEN | KP01 | 12 | Process | Curbstone, curb castings | Base layer, gravel, and curb concrete. | Under construction | Visual | Photo, measurement, placement | 75 % |  | EN
KP01_13_ProcessEN | KP01 | 13 | Process | Straightness, joint widths, flatness | Compliance with the specifications of the project materials and supplier usage. | Under construction | Visual, measurement | Photo, measurement, placement | 75 % |  | EN
KP01_14_ProcessEN | KP01 | 14 | Process | Additional documentation | Functional testing | Under construction | Visual, measurement | Photo | 75 % |  | EN
KP01_15_ProcessEN | KP01 | 15 | Process | Planting, grass, etc. | Compliance with the specifications of the project materials and supplier usage. | Under construction | Visual, measurement | Photo and measurement | 75 % |  | EN
KP01_16_ProcessEN | KP01 | 16 | Process | Inventory in terrain, including sheds. | According to. the project materials, and according to the supplier's instructions. | Under construction | Visual, measurement | Photo and measurement | 75 |  | EN
KP01_17_FinalEN | KP01 | 17 | Final | All building components that are part of the permanent construction and have been part of the contract. | No damages, flawless construction must be delivered within the supplier's instructions, and where the boundary lies. | Submission Final submission and handover | Visual/measurement | Photo | 100 % |  | EN
KP01_18_FinalEN | KP01 | 18 | Final | Cleanup and final submission | Abandoned areas and surfaces have been cleaned by the contractor. | Submission Final submission and handover | Visual | Photo | 100 % |  | EN
KP01_19_FinalEN | KP01 | 19 | Final | Submission of documentation | DMR report, final declaration from authorized sewer master, functional testing. Master review. | Submission Final submission and handover | Sent via email. | Signed | 100 % |  | EN
KP02_1_ProcessEN | KP02 | 1 | Process | Drainage Supply - Control before startup | Control of curbstones, road, in excavated areas where work is intended. | At startup | Visual, measurement | Photo | 100 % |  | EN
KP02_2_ProcessEN | KP02 | 2 | Process | Drainage Supply - Control during execution | Depth for burial, deck bands, fill material, panels, cabinets, manholes | Under Execution | Visual, measurement | Photo | 50 % |  | EN
KP02_3_ProcessEN | KP02 | 3 | Process | Drainage Supply - Transfer of areas. Final inspection/delivery | Control is carried out to ensure that surfaces are delivered level, sown, and surplus material has been removed. | Upon completion notification | Visual | Photo/measurement/drawing | 100 % |  | EN
KP02_4_ProcessEN | KP02 | 4 | Process | electrical supply - Control before startup | Control of curbstones, road, in excavated areas where work is intended. | At startup | Visual, measurement | Photo | 100 % |  | EN
KP02_5_ProcessEN | KP02 | 5 | Process | electrical supply - Control during execution | Depth for burial, deck bands, fill material, panels, cabinets, manholes | Under Execution | Visual, measurement | Photo | 50 % |  | EN
KP02_6_ProcessEN | KP02 | 6 | Process | electrical supply - Transfer of areas. Final inspection/delivery | Control is carried out to ensure that surfaces are delivered level, sown, and surplus material has been removed. | Upon completion notification | Visual | Photo/measurement/drawing | 100 % |  | EN
KP02_7_ProcessEN | KP02 | 7 | Process | water supply - Control before startup | Control of curbstones, road, in excavated areas where work is intended. | At startup | Visual, measurement | Photo | 100 % |  | EN
KP02_8_ProcessEN | KP02 | 8 | Process | water supply - Control during execution | Depth for burial, deck bands, fill material, panels, cabinets, manholes | Under Execution | Visual, measurement | Photo | 50 % |  | EN
KP02_9_ProcessEN | KP02 | 9 | Process | water supply - Transfer of areas. Final inspection/delivery | Control is carried out to ensure that surfaces are delivered level, sown, and surplus material has been removed. | Upon completion notification | Visual | Photo/measurement/drawing | 100 % |  | EN
KP02_10_ProcessEN | KP02 | 10 | Process | district heating - Control before startup | Control of curbstones, road, in excavated areas where work is intended. | At startup | Visual, measurement | Photo | 100 % |  | EN
KP02_11_ProcessEN | KP02 | 11 | Process | district heating - Control during execution | Depth for burial, deck bands, fill material, panels, cabinets, manholes | Under Execution | Visual, measurement | Photo | 50 % |  | EN
KP02_12_ProcessEN | KP02 | 12 | Process | district heating - Transfer of areas. Final inspection/delivery | Control is carried out to ensure that surfaces are delivered level, sown, and surplus material has been removed. | Upon completion notification | Visual | Photo/measurement/drawing | 100 % |  | EN
KP02_13_ProcessEN | KP02 | 13 | Process | fiber/telephone - Control before startup | Control of curbstones, road, in excavated areas where work is intended. | At startup | Visual, measurement | Photo | 100 % |  | EN
KP02_14_ProcessEN | KP02 | 14 | Process | fiber/telephone - Control during execution | Depth for burial, deck bands, fill material, panels, cabinets, manholes | Under Execution | Visual, measurement | Photo | 50 % |  | EN
KP02_15_ProcessEN | KP02 | 15 | Process | fiber/telephone - Transfer of areas. Final inspection/delivery | Control is carried out to ensure that surfaces are delivered level, sown, and surplus material has been removed; panels and manholes are plumb/level. | Upon completion notification | Visual | Photo/measurement/drawing | 100 % |  | EN
KP03_1_ReceiveEN | KP03 | 1 | Receive | All materials and products that are part of the permanent structure | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP03_2_ReceiveEN | KP03 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP03_3_ReceiveEN | KP03 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, boundaries, Levels and measurements, plumb, level | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP03_4_ProcessEN | KP03 | 4 | Process | Setting out - Placement | Must be delivered according to project materials, measurements, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP03_5_ProcessEN | KP03 | 5 | Process | Excavation (depth) | Must be delivered according to project materials, goal, width, height, and must follow geotechnical report. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP03_6_ProcessEN | KP03 | 6 | Process | Reinforcement - dimensions, cover layer, quantity, placement, overlap | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_7_ProcessEN | KP03 | 7 | Process | Anchor rods - dimensions, quantity, placement, length | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_8_ProcessEN | KP03 | 8 | Process | Joint tape (waterproofing) - fastenings, placement | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_9_ProcessEN | KP03 | 9 | Process | Embedded parts - placement, design | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_10_ProcessEN | KP03 | 10 | Process | Cutouts - fastening, placement | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_11_ProcessEN | KP03 | 11 | Process | Casting joints | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_12_ProcessEN | KP03 | 12 | Process | Casting - layers, vibration | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_13_ProcessEN | KP03 | 13 | Process | Covering - placement, tightness | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_14_ProcessEN | KP03 | 14 | Process | Foundation height and shafts | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_15_ProcessEN | KP03 | 15 | Process | In-situ casting on site. | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_16_ProcessEN | KP03 | 16 | Process | Freestanding protrusions are marked/protected | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_17_ProcessEN | KP03 | 17 | Process | Radon barrier | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_18_ProcessEN | KP03 | 18 | Process | Formwork | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_19_ProcessEN | KP03 | 19 | Process | Thermal blocks other blocks/ finishing foundation. | Must be delivered according to project materials, goal, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_20_ProcessEN | KP03 | 20 | Process | Plinth plaster | Must be delivered in accordance with project materials and follow the supplier's instructions | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP03_21_FinalEN | KP03 | 21 | Final | Levels/surfaces | Must be delivered in accordance with project materials, goals, standards, tolerances, etc. | At process changes | Visual, measurement | Photo | 100 % |  | EN
KP03_22_FinalEN | KP03 | 22 | Final | Master review | Must be delivered in accordance with project materials, goals, standards, tolerances, etc. | Completion notification of foundations | Visual, measurement | Photo | 100 % |  | EN
KP04_1_ReceiveEN | KP04 | 1 | Receive | All materials and products that are part of the permanent structure | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP04_2_ReceiveEN | KP04 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP04_3_ReceiveEN | KP04 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces is conducted, Levels and measurements, plumb, measurements | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP04_4_ProcessEN | KP04 | 4 | Process | Insulation (overlap, flatness, closure at penetrations) | Must be delivered according to project materials, measurements, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP04_5_ProcessEN | KP04 | 5 | Process | Formwork | Must be delivered according to project materials, measurements, width, height, and must follow geotechnical reports. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP04_6_ProcessEN | KP04 | 6 | Process | Embedded parts - placement, design | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_7_ProcessEN | KP04 | 7 | Process | Cutouts - Fastening, placement | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_8_ProcessEN | KP04 | 8 | Process | Casting edge | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_9_ProcessEN | KP04 | 9 | Process | Covering - placement, tightness | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_10_ProcessEN | KP04 | 10 | Process | Reinforcement - dimensions, cover layers, quantity, placement, overlap | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_11_ProcessEN | KP04 | 11 | Process | Edge insulation | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_12_ProcessEN | KP04 | 12 | Process | Radon barrier (penetrations, foundations) | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_13_ProcessEN | KP04 | 13 | Process | Expansion joint | Dimension, placement, cover layers, and type must be checked | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_14_ProcessEN | KP04 | 14 | Process | Sound joint | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo/ and documentation | 25 % |  | EN
KP04_15_ProcessEN | KP04 | 15 | Process | Crack indicator | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP04_16_FinalEN | KP04 | 16 | Final | All surfaces/ joints, levels, cutouts | Must be delivered according to project materials, measurements, standards, tolerances, etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP04_17_FinalEN | KP04 | 17 | Final | Master review | Must be delivered according to project materials, measurements, standards, tolerances, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP05_18_ReceiveEN | KP05 | 18 | Receive | All materials and products that are part of the permanent structure | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP05_1_ReceiveEN | KP05 | 1 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP05_2_ReceiveEN | KP05 | 2 | Receive | Takeover of areas after another supplier | Control of surfaces, interfaces is carried out, Levels and measurements, plumb. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP05_3_ProcessEN | KP05 | 3 | Process | Shimming All prefabricated elements. | Must be delivered according to project materials, measurements, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP05_4_ProcessEN | KP05 | 4 | Process | Placement (Tight tolerance) All prefabricated elements. | Must be delivered according to project materials, measurements, width, height, and must follow geotechnical report. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP05_5_ProcessEN | KP05 | 5 | Process | Plumb (Tight tolerance) All prefabricated elements. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_6_ProcessEN | KP05 | 6 | Process | Transitions/Joints (Tight tolerance) All prefabricated elements. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_7_ProcessEN | KP05 | 7 | Process | Casting edge All prefabricated elements. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_8_ProcessEN | KP05 | 8 | Process | Elements/levels on holes Concrete columns. All prefabricated elements. | Must be delivered according to project materials, measurements, standards, tolerances, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_9_ProcessEN | KP05 | 9 | Process | Staircase and Concrete stairs. All prefabricated elements. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_10_ProcessEN | KP05 | 10 | Process | Composite beams Filling, supports, etc. TTS beams. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_11_ProcessEN | KP05 | 11 | Process | Underpinning/Joining (horizontal, vertical) All prefabricated elements. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_12_ProcessEN | KP05 | 12 | Process | Casting components | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_13_ProcessEN | KP05 | 13 | Process | Bracing All prefabricated elements. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_14_ProcessEN | KP05 | 14 | Process | Joint reinforcement All prefabricated elements. | Dimension, placement, cover layer, and type must be checked | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_15_ProcessEN | KP05 | 15 | Process | Certification, when welding. Where there are requirements for it. Steel columns, Beam Type. Dim. | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo/ and documentation | 25 % |  | EN
KP05_16_ProcessEN | KP05 | 16 | Process | Joints | Must be delivered according to project materials, measurements, standards, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP05_17_ProcessEN | KP05 | 17 | Process | Screening and safety | Must be performed safely and in accordance with applicable legislation | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP05_18_FinalEN | KP05 | 18 | Final | All surfaces/ joints, levels, drainage of elements | Must be delivered according to project materials, measurements, standards, tolerances, etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP05_19_FinalEN | KP05 | 19 | Final | Master review | Must be delivered according to project materials, measurements, standards, tolerances, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP06_1_ReceiveEN | KP06 | 1 | Receive | All materials and products that are part of the permanent structure | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP06_2_ReceiveEN | KP06 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP06_3_ReceiveEN | KP06 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces, Levels and measurements, plumb, measurements | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP06_4_ProcessEN | KP06 | 4 | Process | Placement of blocks or elements | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP06_5_ProcessEN | KP06 | 5 | Process | Flatness | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP06_6_ProcessEN | KP06 | 6 | Process | Adhesives | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_7_ProcessEN | KP06 | 7 | Process | Fasteners/brackets etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_8_ProcessEN | KP06 | 8 | Process | Connection at floor/ceiling/roof | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_9_ProcessEN | KP06 | 9 | Process | Plumb | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_10_ProcessEN | KP06 | 10 | Process | Placement of lintel | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_11_ProcessEN | KP06 | 11 | Process | Door/window frames | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_12_ProcessEN | KP06 | 12 | Process | Bracing | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP06_13_FinalEN | KP06 | 13 | Final | All surfaces/ joints, levels, drainage of elements | Must be delivered according to project materials, measurements, standards, tolerances etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP06_14_FinalEN | KP06 | 14 | Final | Master Review | Must be delivered according to project materials, measurements, standards, tolerances etc. | Completion Notification of Assembly | Visual, measurement | Photo | 100 % |  | EN
KP07_1_ReceiveEN | KP07 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP07_2_ReceiveEN | KP07 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP07_3_ReceiveEN | KP07 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, interfaces, Levels and measurements, level, measurements | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP07_4_ProcessEN | KP07 | 4 | Process | Suspended ceilings (Fixed) system | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP07_5_ProcessEN | KP07 | 5 | Process | Formwork type/fixings, vapor barrier, executions, sleeve | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP07_6_ProcessEN | KP07 | 6 | Process | Flatness | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_7_ProcessEN | KP07 | 7 | Process | Fixings/brackets etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_8_ProcessEN | KP07 | 8 | Process | Connection at walls and other building parts | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_9_ProcessEN | KP07 | 9 | Process | Ceiling material/partitioning | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_10_ProcessEN | KP07 | 10 | Process | Documentation for fixing of Gypsum boards/or other ceiling material. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_11_ProcessEN | KP07 | 11 | Process | Installation of fire, sound, and wet room doors, including frames, joints. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_12_ProcessEN | KP07 | 12 | Process | Installation of inspection hatches, ceiling hatches, including. frames skylights etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_13_ProcessEN | KP07 | 13 | Process | Installation of interior doors including. frames, joints, door handles, door stops. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_14_ProcessEN | KP07 | 14 | Process | Installation of interior. partitions (non-load bearing) (steel or wood) including cladding material. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_15_ProcessEN | KP07 | 15 | Process | Installation of interior. partition (load-bearing) in (steel or wood) including cladding materials | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_16_ProcessEN | KP07 | 16 | Process | Installation of interior. partitions, fire or sound walls including cladding materials | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_17_ProcessEN | KP07 | 17 | Process | Installation of facades, suspended on underlying construction. Insulation, wind barrier, ventilation gap, cladding, overlap, etc. External finishing profiles | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_18_ProcessEN | KP07 | 18 | Process | Installation of lightweight facades Insulation, wind barrier, ventilation gap, cladding, overlap, etc. External finishing profiles | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_19_ProcessEN | KP07 | 19 | Process | Flatness on facade, plumb, level indication. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_20_ProcessEN | KP07 | 20 | Process | Installation of doors and window units in external walls, including all types, stops, ready for sealing. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_21_ProcessEN | KP07 | 21 | Process | Installation of prefabricated solutions in the form of steel or wood elements, including both external walls and roof cassettes, dormers. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_22_ProcessEN | KP07 | 22 | Process | Assembly of prefabricated solutions such as beams, walkways, rafters, fences, waste shelters, etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_23_ProcessEN | KP07 | 23 | Process | Underlay, base plate, wind barrier, wind braces, insulation of roof structure, ventilation for roof structure. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_24_ProcessEN | KP07 | 24 | Process | Roof battens, formwork, roof covering, executions, skylights | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_25_ProcessEN | KP07 | 25 | Process | Fire closures, fire walls, fire gables. Apartment boundaries, fire coverings, fire joints. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_26_ProcessEN | KP07 | 26 | Process | Vapor barrier Including external walls and ceilings | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_27_ProcessEN | KP07 | 27 | Process | Exchanges, timber and steel construction (system) | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_28_ProcessEN | KP07 | 28 | Process | Timber construction Structures in terrain such as wooden terraces, bulkheads, walkways, garden houses, orangery, etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_29_ProcessEN | KP07 | 29 | Process | Formwork work, in connection with casting formwork or other good purposes. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_30_ProcessEN | KP07 | 30 | Process | Safety barriers | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_31_ProcessEN | KP07 | 31 | Process | Glass barriers, railings | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_32_ProcessEN | KP07 | 32 | Process | Finishing profiles. Baseboards, transition strips, at doors, aluminum profile, finishes, and edge delimitations. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP07_33_FinalEN | KP07 | 33 | Final | All surfaces building components, materials, and products included in the permanent structure | Must be delivered according to project materials, measurements, standards, tolerances, and applicable legislation, etc. | Upon final assembly | Visual, measurement | Photo | 100 % |  | EN
KP07_34_FinalEN | KP07 | 34 | Final | Master review | Must be delivered according to project materials, measurements, standards, tolerances, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP08_1_ReceiveEN | KP08 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP08_2_ReceiveEN | KP08 | 2 | Receive | Errors and damages on deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_3_ReceiveEN | KP08 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces is carried out, Levels and measurements, plumb. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP08_4_ProcessEN | KP08 | 4 | Process | Ceilings. | Must be delivered according to the project materials, including measurements. According to supplier used, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP08_5_ProcessEN | KP08 | 5 | Process | Facade system Metal and Stone materials, others. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP08_6_ProcessEN | KP08 | 6 | Process | Glass or Glass facade system | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP08_7_ProcessEN | KP08 | 7 | Process | Solar shading and awnings | Must be delivered according to the project materials, including measurements. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP08_8_ProcessEN | KP08 | 8 | Process | Underfloor system Complete. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 45 % |  | EN
KP08_9_ProcessEN | KP08 | 9 | Process | Floor system (finished concept) Sports halls, fitness, other industries | Must be delivered according to the project materials, including measurements. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP08_10_ProcessEN | KP08 | 10 | Process | Major appliances Type, functional testing, connection. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP08_11_ProcessEN | KP08 | 11 | Process | Other furniture such as Furniture, room division, shelves, etc. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP08_12_ProcessEN | KP08 | 12 | Process | Emergency exits (multi-story buildings) Access away in relation to fire. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_13_ProcessEN | KP08 | 13 | Process | Elevator and handicap access. Systems and types are specified. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_14_ProcessEN | KP08 | 14 | Process | Doors and fire doors Type and functional testing. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_15_ProcessEN | KP08 | 15 | Process | Automatic doors, escalators, sluices, etc. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_16_ProcessEN | KP08 | 16 | Process | Signs, banners, etc. Advertising, light signs, others. Product instructions. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_17_ProcessEN | KP08 | 17 | Process | Fencing, fences around property or premises. Type, model | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_18_ProcessEN | KP08 | 18 | Process | Sealing. External and internal joints Backstop, joint felt, etc. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP08_19_FinalEN | KP08 | 19 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered according to project materials, dimensions, standards, tolerances, and applicable legislation, etc., and cleaned. | At the end of assembly | Visual, measurement | Photo | 100 % |  | EN
KP08_20_FinalEN | KP08 | 20 | Final | Master review of all work must, as a general rule, be delivered without defects. | Must be delivered in accordance with project materials, goals, standards, tolerances, and delivered without defects, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP09_1_ReceiveEN | KP09 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project material and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP09_2_ReceiveEN | KP09 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP09_3_ReceiveEN | KP09 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, interfaces, Levels and dimensions, plumb, measurements | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP09_4_ProcessEN | KP09 | 4 | Process | Bases, plumb, fastenings, etc. | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP09_5_ProcessEN | KP09 | 5 | Process | Flatness in fronts. Plumb, skewness | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP09_6_ProcessEN | KP09 | 6 | Process | Cutouts and seals, tabletops, handles. | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP09_7_ProcessEN | KP09 | 7 | Process | Cuttings, penetrations. | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP09_8_ProcessEN | KP09 | 8 | Process | Waste systems, drawers. | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 45 % |  | EN
KP09_9_ProcessEN | KP09 | 9 | Process | Finishing profiles Sand strips at the base, trim strips at tabletops, joints. | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP09_10_ProcessEN | KP09 | 10 | Process | Other furniture such as Furniture, room division, shelves, etc. | Must be delivered according to project material, dimensions. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP09_11_FinalEN | KP09 | 11 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered in accordance with project material, dimensions, standards, tolerances, and applicable legislation, etc. | Upon final assembly | Visual, measurement | Photo | 100 % |  | EN
KP09_12_FinalEN | KP09 | 12 | Final | Master review of all work must, as a rule, be delivered defect-free. | Must be delivered in accordance with the project material, dimensions, standards, tolerances, and delivered defect-free, etc. | Completion report of assembly | Visual, measurement | Photo | 100 % |  | EN
KP10_1_ReceiveEN | KP10 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP10_2_ReceiveEN | KP10 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction. | During execution | Visual, measurement | Photo | 100 % |  | EN
KP10_3_ReceiveEN | KP10 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, interfaces is carried out, levels and measurements, level. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP10_4_ProcessEN | KP10 | 4 | Process | Routing for ducts, placement. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_5_ProcessEN | KP10 | 5 | Process | Joints, dampers, fire dampers, bends. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_6_ProcessEN | KP10 | 6 | Process | Fastenings to building components | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_7_ProcessEN | KP10 | 7 | Process | Penetrations Walls, ceilings, roof, floor, other. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_8_ProcessEN | KP10 | 8 | Process | Marking and fire closures Other seals. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_9_ProcessEN | KP10 | 9 | Process | Functional testing and commissioning of the system, documentation. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_10_ProcessEN | KP10 | 10 | Process | Installation of systems Correct shimming, level, plumb, noise reduction, etc. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_11_ProcessEN | KP10 | 11 | Process | Separately routed ventilation outside the system, other.. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_12_ProcessEN | KP10 | 12 | Process | Technical Insulation General. | Must be insulated according to project materials, measurements, standards, tolerances, and applicable legislation, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_13_ProcessEN | KP10 | 13 | Process | Sound and Fire Seals All holes must be closed | Must be sealed according to project materials, standards, tolerances, and applicable legislation, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP10_14_FinalEN | KP10 | 14 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered according to project materials, measurements, standards, tolerances, and applicable legislation, etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP10_15_FinalEN | KP10 | 15 | Final | Master review of all work must, as a general rule, be delivered defect-free, with instructions for use to the client. | Must be delivered according to project materials, measurements, standards, tolerances, and delivered defect-free, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP11_1_ReceiveEN | KP11 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project material and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP11_2_ReceiveEN | KP11 | 2 | Receive | Errors and damages in deliveries are discarded. | No damages or errors may be implemented in the construction. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP11_3_ReceiveEN | KP11 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces, Levels and measurements, plumb. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP11_4_ProcessEN | KP11 | 4 | Process | Routing for water, heating hoses, drainage including placement, measurements, height indications, etc. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP11_5_ProcessEN | KP11 | 5 | Process | Collections, bends, floor drains, unidrains, others. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_6_ProcessEN | KP11 | 6 | Process | Fastenings to building components. Routing paths, others. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_7_ProcessEN | KP11 | 7 | Process | Penetrations Walls, ceilings, roof, floor, others. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_8_ProcessEN | KP11 | 8 | Process | Marking and fire closures Other seals, closures after breakthrough. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_9_ProcessEN | KP11 | 9 | Process | Installation of convectors, radiators, heaters. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_10_ProcessEN | KP11 | 10 | Process | Functional testing and pressure testing of system, documentation. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_11_ProcessEN | KP11 | 11 | Process | Installation of heating systems, air to heat pump, exchanger, or others. Correct shimming, level, plumb, probes, sensors, etc. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_12_ProcessEN | KP11 | 12 | Process | Site establishment Including connection, shed, and site water. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_13_ProcessEN | KP11 | 13 | Process | Drain connections. Washing machine, toilet, condensate drain, overflow, drain ventilation over the roof, etc. | Must be delivered according to the project material, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_14_ProcessEN | KP11 | 14 | Process | Installation of suspension system for toilet. | Must be delivered according to the project material, including measurements. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_15_ProcessEN | KP11 | 15 | Process | Installation of toilet, bidet, urinal Or other system | Must be delivered according to the project material, including measurements. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_16_ProcessEN | KP11 | 16 | Process | Shower, faucets, cooker, BWT system, hooks, glass partitioning, Or other utility. | Must be delivered according to the project material, including measurements. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_17_ProcessEN | KP11 | 17 | Process | Outdoor installation, Frost-free faucet, or other. | Must be delivered according to the project material, including measurements. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_18_ProcessEN | KP11 | 18 | Process | Sealing work Performed at sanitary installations, requirements for sound, requirements for fire. | Must be delivered according to project material and legal requirements. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_19_ProcessEN | KP11 | 19 | Process | UV drainage, roof drains, discharge | Must be delivered according to the project material, including measurements. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_20_ProcessEN | KP11 | 20 | Process | Cooling system. Connections, welds, entries, sleeves | Must be delivered according to the project material, including goals, dimensions. According to supplier usage, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_21_ProcessEN | KP11 | 21 | Process | Technical insulation of conduits. Heating, water, cooling. | According to. applicable standards and norms. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_22_ProcessEN | KP11 | 22 | Process | Fire Placement of fire cabinets, risers Hose reel. | According to. applicable standards and norms, regulatory requirements, and project material. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP11_23_FinalEN | KP11 | 23 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered according to the project material, goals, standards, tolerances, and applicable legislation, etc. | Upon final assembly | Visual, measurement | Photo | 100 % |  | EN
KP11_24_FinalEN | KP11 | 24 | Final | Master review of all work must, as a principle, be submitted without defects, instructions for use to BH. | Must be delivered in accordance with project material, goals, standards, tolerances, and delivered defect-free, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP12_1_ReceiveEN | KP12 | 1 | Receive | All materials and products included in the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP12_2_ReceiveEN | KP12 | 2 | Receive | Errors and damages in deliveries are discarded. | No damages or errors may be implemented in the construction. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP12_3_ReceiveEN | KP12 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, interfaces is carried out, Levels and measurements, level. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP12_4_ProcessEN | KP12 | 4 | Process | Routing paths for electrical, control cables, supply cables, placement, measurements, height indications, etc. | Must be delivered according to the project materials, including measurements. According to supplier use, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP12_5_ProcessEN | KP12 | 5 | Process | Main panels, group panels, control panels, supply cabinets, fire control boxes, electrical control in general. Other relevant control. | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_6_ProcessEN | KP12 | 6 | Process | Fastenings to building components. Routing paths, type, withdrawal value on plugs, screws, and others. | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_7_ProcessEN | KP12 | 7 | Process | Penetrations Walls, ceilings, roofs, floors, others. Documentation for closure. | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_8_ProcessEN | KP12 | 8 | Process | Marking and fire closures Other seals, closures after breakthrough. | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_9_ProcessEN | KP12 | 9 | Process | Functional test, testing of system, of AV, ABDL, ABA, Fire. all technical installations, as well as documentation thereof | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_10_ProcessEN | KP12 | 10 | Process | Installation of all technical installations, as defined. Correct shimming, level, plumb, sensors, etc. | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_11_ProcessEN | KP12 | 11 | Process | Site establishment Including connections, shed, lighting on common roads, and outdoor lighting, construction power panels, etc. | Must be delivered in accordance with the project materials and applicable occupational health and safety legislation. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_12_ProcessEN | KP12 | 12 | Process | Connections of electrical equipment. washing machine, dryer, ovens, stove, refrigeration, ventilation, fire alarm, pumps, other necessary equipment, etc. | Must be delivered according to the project materials, including measurements. According to supplier application, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_13_ProcessEN | KP12 | 13 | Process | Installation of suspension systems, cable trays, other retention systems. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_14_ProcessEN | KP12 | 14 | Process | Installation of penetration sleeves in outer walls, ceilings, etc. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_15_ProcessEN | KP12 | 15 | Process | Control systems: fire, ventilation, automation. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_16_ProcessEN | KP12 | 16 | Process | Outdoor installation, Lamp posts, lamps, bollards, switches, others. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_17_ProcessEN | KP12 | 17 | Process | Fire/sound closures (Sealing) Correct markings. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_18_ProcessEN | KP12 | 18 | Process | Monitoring system | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_19_ProcessEN | KP12 | 19 | Process | Control panels | According to. applicable standards and norms. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP12_20_ProcessEN | KP12 | 20 | Process | Equalization connection Main equalization, supplementary equalization connection. Or continuous electrical connection | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_21_ProcessEN | KP12 | 21 | Process | Marking/naming of installations, affiliations, etc. must be clear in panels and on user interfaces. | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_22_ProcessEN | KP12 | 22 | Process | Covering of cables, splices, others in terrain. | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_23_ProcessEN | KP12 | 23 | Process | Insulation measurement. Low voltage, weak current, and 400 V. Values? | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_24_ProcessEN | KP12 | 24 | Process | Lighting in general. Type in relation to application. Enclosure, etc. | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_25_ProcessEN | KP12 | 25 | Process | Control of operation and lighting, connection of installation. | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_26_ProcessEN | KP12 | 26 | Process | Low current installation Specification of type: AV. Antenna, Network, telephone, induction loop system, intercom, video, Alarm, fire alarm, and others. | Must be delivered according to the project materials, including measurements. According to supplier specifications, etc. | [5 empty] | EN
KP12_27_ProcessEN | KP12 | 27 | Process | Measurement reports. AV. Antenna, Network, telephone, induction loop system, intercom, video, Alarm, fire alarm, and others. | According to. applicable standards and norms, legislation, and Project materials. | [5 empty] | EN
KP12_28_FinalEN | KP12 | 28 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered according to project materials, measurements, standards, tolerances, and applicable legislation, regulatory requirements, etc. | Upon final assembly | Visual, measurement | Photo | 100 % |  | EN
KP12_29_FinalEN | KP12 | 29 | Final | Master review of all work must, as a rule, be delivered without defects, with instructions for use to the client. | Must be delivered in accordance with the project materials, measurements, standards, tolerances, and delivered without defects, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP13_1_ReceiveEN | KP13 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project material and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP13_2_ReceiveEN | KP13 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP13_3_ReceiveEN | KP13 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces, Levels and measurements, plumb, measurements | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP13_4_ProcessEN | KP13 | 4 | Process | Underlayment, plywood, boards, battens, spacers Track material. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP13_5_ProcessEN | KP13 | 5 | Process | Insulation Thickness, type, etc. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP13_6_ProcessEN | KP13 | 6 | Process | Ventilation in construction | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_7_ProcessEN | KP13 | 7 | Process | High profiles in steel (trapezoidal) | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_8_ProcessEN | KP13 | 8 | Process | Exchange to high profiles (trapezoidal) | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_9_ProcessEN | KP13 | 9 | Process | Support profiles for high profiles (trapezoidal) Dim. type, height, etc. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_10_ProcessEN | KP13 | 10 | Process | Vapor barrier system Type designation. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_11_ProcessEN | KP13 | 11 | Process | Slope construction with insulation (flat roofs). Type, model | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_12_ProcessEN | KP13 | 12 | Process | Ridge lights, skylights | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_13_ProcessEN | KP13 | 13 | Process | Wall crown, and fire wall connection or apartment boundary. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_14_ProcessEN | KP13 | 14 | Process | Finishing profiles Loose edge, eaves profiles, other finishes. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_15_ProcessEN | KP13 | 15 | Process | Roofing felt and drainage Type designation Correctly placed, overlaps, etc. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_16_ProcessEN | KP13 | 16 | Process | Roof safety Roof safety line. Guard and shielding | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_17_ProcessEN | KP13 | 17 | Process | Roof covering: Including slate, metal roof, brick, concrete tiles, wood shingles, green roof (Moss sedum) | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_18_ProcessEN | KP13 | 18 | Process | Roof covering: Ridges, binders, bird stops Snow slide safety, roof caps, edge profiles, finishing stones. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_19_ProcessEN | KP13 | 19 | Process | Roof terrace: Paving stones, wooden terrace Substructure construction. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_20_ProcessEN | KP13 | 20 | Process | Glass roof: Including sun shading, safety, etc. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_21_ProcessEN | KP13 | 21 | Process | Access route to the roof. | Must be delivered according to the project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP13_22_FinalEN | KP13 | 22 | Final | All surfaces building components, materials and products included in the permanent structure | Must be delivered in accordance with the project material, goal, standards, tolerances, and applicable legislation, etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP13_23_FinalEN | KP13 | 23 | Final | Master review | Must be delivered in accordance with the project material, goal, standards, tolerances, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP14_1_ReceiveEN | KP14 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP14_2_ReceiveEN | KP14 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP14_3_ReceiveEN | KP14 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces, Levels and measurements, plumb, tolerances. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP14_4_ProcessEN | KP14 | 4 | Process | Moisture measurement of subfloors control results | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP14_5_ProcessEN | KP14 | 5 | Process | Adhesion ability Control. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP14_6_ProcessEN | KP14 | 6 | Process | Boundaries between coverings. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_7_ProcessEN | KP14 | 7 | Process | Floor types, wood and others. As used. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_8_ProcessEN | KP14 | 8 | Process | Designer floor. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_9_ProcessEN | KP14 | 9 | Process | Primer and thin layer Type designation | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_10_ProcessEN | KP14 | 10 | Process | Welds and transitions Types and model. DVK control of welding. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_11_ProcessEN | KP14 | 11 | Process | Adhesion | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_12_ProcessEN | KP14 | 12 | Process | Vinyl and linoleum types Height indications on edges, types, etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_13_ProcessEN | KP14 | 13 | Process | Installation of drains in wet rooms | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_14_ProcessEN | KP14 | 14 | Process | Covering on stairs and access paths. Type designation | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_15_ProcessEN | KP14 | 15 | Process | Skirting boards, or other finishing strips at walls. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_16_ProcessEN | KP14 | 16 | Process | Joints and expansion joints or rails. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_17_ProcessEN | KP14 | 17 | Process | Surface treatment Lacquer, wax, topcoat, oil | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_18_ProcessEN | KP14 | 18 | Process | Subfloor construction (Wood) joists, moisture barrier, insulation, air at walls. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_19_ProcessEN | KP14 | 19 | Process | Baseboards Type specified, and fastenings | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_20_ProcessEN | KP14 | 20 | Process | Acoustic fabric Placement, and up to apartment boundaries. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_21_ProcessEN | KP14 | 21 | Process | Recessed mat Type, dimensions. Height, and placement | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_22_ProcessEN | KP14 | 22 | Process | Covering of areas | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP14_23_FinalEN | KP14 | 23 | Final | All surfaces building components, materials and products included in the permanent structure | Must be delivered in accordance with project materials, measurements, standards, tolerances, and applicable legislation, etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP14_24_FinalEN | KP14 | 24 | Final | Master review | Must be delivered in accordance with project materials, measurements, standards, tolerances, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP15_1_ReceiveEN | KP15 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP15_2_ReceiveEN | KP15 | 2 | Receive | Errors and damages on deliveries are discarded | No damages or errors may be implemented in the construction | During execution | Visual, measurement | Photo | 100 % |  | EN
KP15_3_ReceiveEN | KP15 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, boundaries, Levels and measurements, openings, falsework. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP15_4_ProcessEN | KP15 | 4 | Process | Filling and reinforcement of joints, corners, duct boxes, openings, etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_5_ProcessEN | KP15 | 5 | Process | Covering and followed up | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_6_ProcessEN | KP15 | 6 | Process | Full plastering of hard walls and ceilings (concrete) or lightweight concrete | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_7_ProcessEN | KP15 | 7 | Process | Full plastering of lightweight walls Board products, gypsum, etc. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_8_ProcessEN | KP15 | 8 | Process | Grind all surfaces | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_9_ProcessEN | KP15 | 9 | Process | Primer. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_10_ProcessEN | KP15 | 10 | Process | Wallpaper/ or other roll goods | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_11_ProcessEN | KP15 | 11 | Process | Acrylic joints, ceiling, walls, adjacent walls, and at moldings. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_12_ProcessEN | KP15 | 12 | Process | Painting of interior surfaces at least 2 times. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_13_ProcessEN | KP15 | 13 | Process | Grinding and preparation of woodwork. Priming | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_14_ProcessEN | KP15 | 14 | Process | Painting of all interior woodwork | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_15_ProcessEN | KP15 | 15 | Process | Cleaning and priming of exterior woodwork. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_16_ProcessEN | KP15 | 16 | Process | Painting of exterior woodwork. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_17_ProcessEN | KP15 | 17 | Process | Final treatment before handover Interior. | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_18_ProcessEN | KP15 | 18 | Process | Final cleaning of all surfaces Window cleaning, | Must be delivered according to project materials, measurements. According to supplier specifications, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP15_19_FinalEN | KP15 | 19 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered in accordance with the project materials, measurements, standards, tolerances, and applicable legislation, etc. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP15_20_FinalEN | KP15 | 20 | Final | Master review of all work must, as a general rule, be delivered defect-free. | Must be delivered in accordance with the project materials, measurements, standards, tolerances, and delivered defect-free, etc. | Completion notification | Visual, measurement | Photo | 100 % |  | EN
KP16_1_ReceiveEN | KP16 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project material and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP16_2_ReceiveEN | KP16 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP16_3_ReceiveEN | KP16 | 3 | Receive | Taking over areas after another supplier | Control of surfaces, interfaces, Levels and measurements, level, tolerances. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP16_4_ProcessEN | KP16 | 4 | Process | Standards and approvals Storage on site | Must be delivered according to project material, measurements. According to supplier specifications, etc. | Before casting | Visual, measurement | Photo | 100 % |  | EN
KP16_5_ProcessEN | KP16 | 5 | Process | DS/EN ISO 3834-2 Quality Requirements for fusion welding of metallic materials – Complete quality requirements | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP16_6_ProcessEN | KP16 | 6 | Process | DS/EN ISO 3834-4 Quality Requirements for fusion welding of metallic materials – Elementary quality requirements | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_7_ProcessEN | KP16 | 7 | Process | DS/EN ISO 9606-1 Qualification of welders – Fusion welding – Part A: Steel | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_8_ProcessEN | KP16 | 8 | Process | DS/EN ISO 9606-2 Qualification of welders – Fusion welding – Part B: Aluminum | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_9_ProcessEN | KP16 | 9 | Process | DS/EN ISO 9606-3 Qualification of welders – Fusion welding – Part C: Copper | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_10_ProcessEN | KP16 | 10 | Process | Welds and transitions Types and model. VK control of welder. | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_11_ProcessEN | KP16 | 11 | Process | DS/EN ISO 9606-4 Qualification of welders – Fusion welding – Part 4: Nickel | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_12_ProcessEN | KP16 | 12 | Process | DS/EN ISO 9606-5 Qualification of welders – Fusion welding – Part 5: Titanium and zirconium | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_13_ProcessEN | KP16 | 13 | Process | DS/EN ISO 14732 Welding personnel – Qualification of welding operators and welding setters for mechanized and automated welding of metallic materials. | Must be delivered according to project material, measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_14_ProcessEN | KP16 | 14 | Process | Steel beams Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_15_ProcessEN | KP16 | 15 | Process | Steel brackets, angles Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_16_ProcessEN | KP16 | 16 | Process | Steel stringers Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_17_ProcessEN | KP16 | 17 | Process | Inserted steel decks Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_18_ProcessEN | KP16 | 18 | Process | Steel stairs and landings Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_19_ProcessEN | KP16 | 19 | Process | Steel balconies Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_20_ProcessEN | KP16 | 20 | Process | Ground-level steel sheds Specification of type, dimension, surface treatment | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_21_ProcessEN | KP16 | 21 | Process | Railings and barriers in steel Specification of type, dimension, surface treatment. | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_22_ProcessEN | KP16 | 22 | Process | Thin plate steel, profiles Specification of type, dimension, surface treatment. | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_23_ProcessEN | KP16 | 23 | Process | Fastening components Specification of type, dimension, length, surface treatment. | Must be delivered according to project material, measurements. According to supplier instructions, plumb, level, tolerances | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP16_24_FinalEN | KP16 | 24 | Final | All surfaces building components, materials, and products included in the permanent structure | Must be delivered in accordance with project material, measurements, standards, tolerances, and applicable legislation, etc. | Upon final assembly | Visual, measurement | Photo | 100 % |  | EN
KP16_25_FinalEN | KP16 | 25 | Final | Master review | Must be delivered in accordance with project material, measurements, standards, tolerances, etc. | Completion report of assembly | Visual, measurement | Photo | 100 % |  | EN
KP17_1_ReceiveEN | KP17 | 1 | Receive | All materials and products included in the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP17_2_ReceiveEN | KP17 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP17_3_ReceiveEN | KP17 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, boundaries, levels and measurements, plumb. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP17_4_ProcessEN | KP17 | 4 | Process | Moisture barrier (clamping rail, sealing) Base plaster | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | Under execution | Visual, measurement | Photo | 25 % |  | EN
KP17_5_ProcessEN | KP17 | 5 | Process | Insulation and cavities | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_6_ProcessEN | KP17 | 6 | Process | Binders | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_7_ProcessEN | KP17 | 7 | Process | Thermal bridge insulation | Must be delivered in accordance with project materials, including measurements. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_8_ProcessEN | KP17 | 8 | Process | Beam supports | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 45 % |  | EN
KP17_9_ProcessEN | KP17 | 9 | Process | Moisture protection over wall openings (windows, doors) | Must be delivered in accordance with project materials, including measurements. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_10_ProcessEN | KP17 | 10 | Process | Sill benches | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_11_ProcessEN | KP17 | 11 | Process | Joint work. | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_12_ProcessEN | KP17 | 12 | Process | Excavation of joints | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_13_ProcessEN | KP17 | 13 | Process | Reinforcement of masonry. Reinforcing steel embedded, etc. | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_14_ProcessEN | KP17 | 14 | Process | Placement of blocks Thermal and lightweight concrete blocks Dimension type specification. | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_15_ProcessEN | KP17 | 15 | Process | Reinforcement in joints | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_16_ProcessEN | KP17 | 16 | Process | Foundation blocks, reinforcement, vertical and horizontal | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_17_ProcessEN | KP17 | 17 | Process | Concrete type Setting measurements and class specified | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_18_ProcessEN | KP17 | 18 | Process | Slope construction, boundaries | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. |  |  |  | 25 % |  | EN
KP17_19_ProcessEN | KP17 | 19 | Process | Preparation for wet rooms | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_20_ProcessEN | KP17 | 20 | Process | Wet room system applied | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. |  |  |  | 25 % |  | EN
KP17_21_ProcessEN | KP17 | 21 | Process | Floor tile assembly Type and bond | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_22_ProcessEN | KP17 | 22 | Process | Grouting of floor tiles | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_23_ProcessEN | KP17 | 23 | Process | Grouting of wall tiles | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_24_ProcessEN | KP17 | 24 | Process | Rubber joints at floor and adjacent walls, niches. | Must be delivered in accordance with project materials, including measurements. According to supplier specifications, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP17_25_FinalEN | KP17 | 25 | Final | All surfaces building components, materials and products included in it permanent structures must be delivered defect-free. | Must be delivered in accordance with project materials, measurements, standards, tolerances, and applicable legislation, etc., and cleaned. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP17_26_FinalEN | KP17 | 26 | Final | Master review of all work must, as a rule, be delivered defect-free. | Must be delivered in accordance with project materials, measurements, standards, tolerances, and delivered defect-free, etc. | Completion notification of assembly | Visual, measurement | Photo | 100 % |  | EN
KP18_1_ReceiveEN | KP18 | 1 | Receive | All materials and products that are part of the permanent structure. | Must follow the project materials and the basis for the contract. | Upon receipt | Visual, measurement | Photo/delivery notes | 100 % |  | EN
KP18_2_ReceiveEN | KP18 | 2 | Receive | Errors and damages in deliveries are discarded | No damages or errors may be implemented in the construction | During Execution | Visual, measurement | Photo | 100 % |  | EN
KP18_3_ReceiveEN | KP18 | 3 | Receive | Takeover of areas after another supplier | Control of surfaces, boundaries, Levels and measurements, plumb. | Upon receipt | Visual, measuring equipment | Photo | 100 % |  | EN
KP18_4_ProcessEN | KP18 | 4 | Process | Installation of drainage bars, distance, etc. | Must be delivered according to project materials, including measurements. According to supplier used, etc. | During execution | Visual, measurement | Photo | 25 % |  | EN
KP18_5_ProcessEN | KP18 | 5 | Process | Installation of gutters Including definition of metal type, slope, etc. | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_6_ProcessEN | KP18 | 6 | Process | Spouts | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_7_ProcessEN | KP18 | 7 | Process | Expansion pieces | Must be delivered according to project materials, including measurements. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_8_ProcessEN | KP18 | 8 | Process | End caps, soldering, etc. | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 45 % |  | EN
KP18_9_ProcessEN | KP18 | 9 | Process | Downspouts/outlets, pipe holders | Must be delivered according to project materials, including measurements. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_10_ProcessEN | KP18 | 10 | Process | Foot plates/overlaps | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_11_ProcessEN | KP18 | 11 | Process | Skirted gutters/overlaps | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_12_ProcessEN | KP18 | 12 | Process | Solder joints | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_13_ProcessEN | KP18 | 13 | Process | False/sizes | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_14_ProcessEN | KP18 | 14 | Process | Light openings, sill bench, etc. | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_15_ProcessEN | KP18 | 15 | Process | Roof covering in Zinc, Copper, other metal, fastenings to substrate | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_16_ProcessEN | KP18 | 16 | Process | Ventilation hoods, ventilation for drainage. | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_17_ProcessEN | KP18 | 17 | Process | Crown moldings in Zinc, Copper, other metal. | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_18_ProcessEN | KP18 | 18 | Process | Edge restrictions | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_19_ProcessEN | KP18 | 19 | Process | Snow slide protection | Must be delivered according to project materials, including measurements. According to supplier use, etc. | During Execution | Visual, measurement | Photo | 25 % |  | EN
KP18_20_FinalEN | KP18 | 20 | Final | All surfaces building components, materials, and products included in the permanent structure must be delivered defect-free. | Must be delivered in accordance with project materials, measurements, standards, tolerances, applicable legislation, etc., and cleaned. | At final assembly | Visual, measurement | Photo | 100 % |  | EN
KP18_21_FinalEN | KP18 | 21 | Final | Master review of all work must, as a general rule, be delivered defect-free. | Must be delivered according to project materials, measurements, standards, tolerances, and delivered defect-free, etc. | Completion report of assembly | Visual, measurement | Photo | 100 % |  | EN
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__
__

## DropDownMenu_Language
Language
EN
DK
DE
PL
FR
ES
PT
NO
SE
IT

## DropDownMenu_DocReq
Documentation Requirements
Photo
Photo, measurement, placement
Photo and measurement
Signed
Photo/measurement/drawing
Photo/delivery notes
Photo/ and documentation

## DropDownMenu_Method
Method
Visual
Visual, measurement
Visual/measurement
Sent via email.
Visual, measuring equipment

## DropDownMenu_Time
Time
Weekly Inspection
Upon delivery
Upon takeover of boundary surfaces
Upon receipt
Under construction
Submission Final submission and handover
At startup
Under Execution
Upon completion notification
During Execution
Before casting
At process changes
Completion notification of foundations
At final assembly
Completion notification of assembly
Upon final assembly
At the end of assembly
Completion report of assembly
Completion notification

## DropDownMenu_Type
Type
Other
Receive
Process
Final
Drainage Supply
electrical supply
water supply
district heating
fiber/telephone

## DropDownMenu_SubjectMatters
SubjectMatterId | GroupName | Language
KP00 | Work Environment and Safety | EN
KP01 | SOIL, SEWER, AND FACILITIES | EN
KP02 | Supply work in soil | EN
KP03 | Foundations_Concrete | EN
KP04 | Foundation slab | EN
KP05 | Concrete elements | EN
KP06 | Light Concrete_Aerated Concrete_Silica Blocks | EN
KP07 | Carpenter | EN
KP08 | System deliveries | EN
KP09 | Furniture and fittings etc | EN
KP10 | Ventilation | EN
KP11 | HVAC_Water_heating_sanitation | EN
KP12 | Electrical Installations | EN
KP13 | Roof covering | EN
KP14 | Flooring/installation | EN
KP15 | Painting_spackling | EN
KP16 | Steel_and deliveries | EN
KP17 | Mason worker | EN
KP18 | PLUMBER | EN
KP19 |  | EN
KP20 |  | EN
KP21 |  | EN
KP22 |  | EN
KP23 |  | EN