## Static_checklist
|  |  |  | Static Kontrolplan |  | DS1140 |  | Data comes from app
REVIEW OF THE EXECUTION BASIS FROM DESIGN
[7 empty] | If 1 or 2 = 10% if 3 or 4 then 20% |  |  |  |  | Only when 4
DS_GroupId | SubjectMatterId | ItemId | Contol of | Subject | Construction part | Basis | Control methode | extent | Acceptance criteria | Time | Self control | Independent inspektion | 3rd party inspection
B1 | Default | 7.1.1 | Working drawings, instructions. | Control of project materials | Construction section | Documented self-control. | Review Examination of basis, visual | 100% | There is a self-control report for the review of whether the basis contains sufficient information for correct execution, including placements and tolerances | Before the work begins | Name/ID | Name/ID | Name/ID
B1 | Default | 7.1.2 | Working drawings, instructions, and assembly guidelines for buildability | Control of whether self-control has been carried out on information in working drawings, instructions, and assembly instructions | Construction section | Documented self-control. | Review Examination of basis, visual | 100% | There is a self-control report for the review of whether,the basis for the work is in accordance with the basis from the design | Before the work begins | Name/ID | Name/ID | Name/ID
B1 | Default | 7.1.3 | Work environment regulations | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control. | Review Examination of basis, visual | 100% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins | Name/ID | Name/ID | Name/ID
B1 | Default | 7.1.4 | Understanding | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control. | Review Examination of basis, visual | 100% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins | Name/ID | Name/ID | Name/ID
B1 | Default | 7.1.5 | Coordination | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control. | Review Examination of basis, visual | 100% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins | Name/ID | Name/ID | Name/ID
B1 | Default | 7.1.6 | Interfaces | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control. | Review Examination of basis, visual | 100% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins | Name/ID | Name/ID | Name/ID
B2 | Default | 7.2.1 | Working drawings, instructions, and assembly guidelines for buildability | Control of whether self-control has been carried out on working drawings, instructions, and assembly instructions | Construction section | Documented self-control | Review Examination of basis, Visual | 10% | There is a self-control report for the review of whether the basis contains sufficient information for correct execution, including placements and tolerances | Before the work begins | Name/ID | Name/ID | Name/ID
B2 | Default | 7.2.2 | Working drawings, instructions, and assembly guidelines for buildability | Control of whether self-control has been carried out on working drawings, instructions, and assembly instructions | Construction section | Documented self-control | Review Examination of basis, Visual | 10% | There is a self-control report for the review of whether the basis for the work is in accordance with the basis from the design | Before the work begins | Name/ID | Name/ID | Name/ID
B2 | Default | 7.2.3 | Work environment regulations | Control of whether self-control has been carried out on working drawings, instructions, and assembly instructions | Construction section | Documented self-control | Review Examination of basis, Visual | 10% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins | Name/ID | Name/ID | Name/ID
B2 | Default | 7.2.4 | Understanding | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control | Review Examination of basis, Visual | 10% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins, there is an understanding of the project's structure and execution method. | Name/ID | Name/ID | Name/ID
B2 | Default | 7.2.5 | Coordination | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control | Review Examination of basis, Visual | 10% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins, coordination has been made with the construction management. | Name/ID | Name/ID | Name/ID
B2 | Default | 7.2.6 | Interfaces | Control of whether the working drawings, assembly instructions, and instructions contain the necessary information and prerequisites for correct work | Construction section | Documented self-control | Review Examination of basis, Visual | 10% | The execution basis for the work contains the necessary information (execution classes, material requirements, and tolerances) and the information is clear, understandable, and accessible | Before the work begins, the interfaces must be aligned. | Name/ID | Name/ID | Name/ID
B3 | Default | 7.3.1 | Purchased materials and products | Control of whether self-control has been conducted on the documentation for materials and products | Construction section | Project material | Review Examination of basis, Visual | 10% | Self-control report documents that control has been conducted to ensure that the documentation for purchased materials and products complies with the requirements specified in the execution basis | Upon deliveries/delivery | Name/ID | Name/ID | Name/ID
B3 | Default | 7.3.2 | Materials and products meet the requirements in project materials | Control of whether self-control has been conducted on the documentation of CE-marked products | Construction section | Project material | Review Examination of basis, Visual | 10% | Self-control report documents that CE documentation exists for harmonized construction products | Upon deliveries/delivery | Name/ID | Name/ID | Name/ID
B3 | Default | 7.3.3 | Specific materials. | Control of the documentation for purchased materials and products for selected parts | Construction section | Product descriptions, performance descriptions, etc. | Visual | 10% | The documentation for selected parts is in accordance with requirements in the execution basis | Before installation | Name/ID | Name/ID | Name/ID
B3 | Default | 7.3.4 | Supplementary components such as. pre-manufactured products that are to be included in the construction | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | Default | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP07 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B4 | Default | 7.4.1 | receiving inspection | Control that self-control of deliveries has been carried out | Construction section | Project material | Visual/delivery note | 10% | The self-control documents that control of materials and products has been carried out, and that storage and handling thereof occurs under conditions that do not damage products and materials | Under execution | Name/ID | Name/ID | Name/ID
B4 | Default | 7.4.2 | Delivery note | Control to ensure that self-control has been performed regarding strength, dimensions, and width, etc. | Construction section | Project material | Visual/photo | 10% | The self-control documents that control has been performed and is in accordance with the project materials | Under execution | Name/ID | Name/ID | Name/ID
B4 | Default | 7.4.3 | Delivery | Control to ensure that self-control has been performed on deliveries | Construction section | Thickness, length, and quality, place of use, etc. | Visual | 10% | The self-control documents that control has been performed on the placement of components and is in accordance with the execution basis | Upon receipt | Name/ID | Name/ID | Name/ID
B5 | Default | 7.5.1 | Transport and storage on site | Control to ensure that self-control has been performed regarding handling and storage of materials on the construction site. | Construction section | Project material | Visual, possibly photo | 10% | The self-control documents that control of materials and products has been carried out, and that storage and handling thereof occurs under conditions that do not damage products and materials | Under execution | Name/ID | Name/ID | Name/ID
B5 | Default | 7.5.2 | Previously executed construction | Control to ensure that self-control has been performed, and control of width, length, and dimensions, correct fastenings Components, other | Construction section | Project material | Visual, possibly photo | 10% | The self-control documents that control has been performed and is in accordance with the project materials, CE marking, types, classifications. | Under execution | Name/ID | Name/ID | Name/ID
B5 | Default | 7.5.3 | Assembly of prefabricated construction parts | Control to ensure that self-control has been performed before placement of components, compensation, overlays, etc. | Construction section | Project material | Visual, possibly photo | 10% | The self-control documents that control has been performed on the placement of components and is in accordance with the execution basis | Under receipt | Name/ID | Name/ID | Name/ID
B5 | Default | 7.5.4 | Execution of non-certified construction parts | Control of non-certified construction parts has been carried out according to the project materials. | Construction section | Project material | Visual, possibly photo | 10% | The self-control documents that control has been performed, and it corresponds with the project materials. | Under execution | Name/ID | Name/ID | Name/ID
B6 | Default | 7.6.1 | Execution and completion of work. | Control to ensure that self-control of the completed work has been carried out is finished. | Construction section | Documented self-control | Visual, possibly photo, measurement. | 100% | The self-control documents that there has been control of the work performed within the tolerances for the completed work and for the nature and scope of the work. | Under execution | Name/ID | Name/ID | Name/ID
B6 | Default | 7.6.2 | Cleanup | Control to ensure that self-control of the worksite has been cleaned and tidied upon completion. | Construction section | Documented self-control | Visual/photo | 100% | The self-control documents that there has been control and that the worksite has been handed over cleaned. | Under execution | Name/ID | Name/ID | Name/ID
B3 | KP00 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP01 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP02 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP03 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP04 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP05 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP06 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP08 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP09 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP10 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP11 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP12 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP13 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP14 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP15 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP16 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP17 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID
B3 | KP18 | 7.3.5 | Selected parts covered by harmonized standard etc. | Control for CE marking of selected parts | Construction section | CE marking and performance declaration | Visual | 10% | Selected timber parts are delivered CE marked where this is a requirement | Before installation | Name/ID | Name/ID | Name/ID

## Deviations
DEVIATION
DS_GroupId | ItemId | Contol of | Subject | Construction part | Basis | Control methode | extent | Acceptance criteria | Time | Self control | Independent inspektion
B7 | 7.7.1 | ADD | ADD | EuroCodeId | ADD | Visual, possibly photo, measurement. | 100% | ADD | Under execution | Name/ID | Name/ID
B7 | 7.7.2 | ADD | ADD | EuroCodeId | ADD | Visual, possibly photo, measurement. | 100% | ADD | Under execution | Name/ID | Name/ID